## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration | Time: Begin | Time: Finish | Time: Resit | Note
Account Management | Update Profile | Medium | Iteration 1 | CE170981 | Bùi Ngọc Huy | Iteration 1 | 2024-02-02 | 2024-09-02 |  | complete
| Change Password | Medium | Iteration 1 | CE170981 | Bùi Ngọc Huy | Iteration 1 | 2024-02-02 | 2024-09-02 |  | complete
Login | Logout | Simple | Iteration 1 | CE171653 | Phan Hoàng Phúc | Iteration 1 | 2024-02-02 | 2024-09-02 |  | complete
| Forget Password | Medium | Iteration 1 | CE171653 | Phan Hoàng Phúc | Iteration 1 | 2024-02-02 | 2024-09-02 |  | complete
| Login | Simple | Iteration 1 | CE171653 | Phan Hoàng Phúc | Iteration 1 | 2024-02-02 | 2024-09-02 |  | complete
Register Account | Register Account | Medium | Iteration 1 | CE171653 | Phan Hoàng Phúc | Iteration 1 | 2024-02-02 | 2024-09-02 |  | complete
Search Product | Search By Name | Simple | Iteration 1 | CS171351 | Nguyễn Thị Ngà | Iteration 1 | 2024-02-02 | 2024-09-02 |  | complete
View Product | View All Product | Simple | Iteration 1 | CE170981 | Bùi Ngọc Huy | Iteration 1 | 2024-02-02 | 2024-09-02 |  | complete
| View Best Seller | Medium | Iteration 2 | CE170981 | Bùi Ngọc Huy | Iteration 2 | 2024-10-02 | 16/2/2024 |  | complete
| View Newest Product | Medium | Iteration 2 | CE171653 | Phan Hoàng Phúc | Iteration 2 | 2024-10-02 | 16/2/2024 |  | complete
Caterory Manager | View Product By Caterory | Simple | Iteration 1 | CS171351 | Nguyễn Thị Ngà | Iteration 1 | 2024-02-02 | 2024-09-02 |  | complete
Sort Product | Filter By Price | Medium | Iteration 2 | CE171653 | Phan Hoàng Phúc | Iteration 2 | 2024-10-02 | 16/2/2024 |  | complete
| Filter By Brand | Simple | Iteration 2 | CS171351 | Nguyễn Thị Ngà | Iteration 2 | 2024-10-02 | 16/2/2024 |  | complete
| Sort By Price | Medium | Iteration 2 | CS171351 | Nguyễn Thị Ngà | Iteration 2 | 2024-10-02 | 16/2/2024 |  | complete
| Sort By Newest Product | Simple | Iteration 2 | CS171351 | Nguyễn Thị Ngà | Iteration 2 | 2024-10-02 | 16/2/2024 |  | complete
| Sort By Letter | Simple | Iteration 2 | CS171351 | Nguyễn Thị Ngà | Iteration 2 | 2024-10-02 | 16/2/2024 |  | complete
Order | Cancel Order | Simple | Iteration 2 | CE161080 | Nguyễn Thanh Quang Duy | Iteration 2 | 2024-10-02 | 16/2/2024 |  | complete
| Buy Product | Medium | Iteration 2 | CE161080 | Nguyễn Thanh Quang Duy | Iteration 2 | 2024-10-02 | 16/2/2024 |  | complete
| View Order List | Simple | Iteration 2 | CE170981 | Bùi Ngọc Huy | Iteration 2 | 2024-10-02 | 16/2/2024 |  | complete
| View Order Details | Simple | Iteration 3 | CE170981 | Bùi Ngọc Huy | Iteration 3 | 17/2/2024 | 23/2/2024 |  | complete
Cart Management | View Product Details | Simple | Iteration 3 | CE170981 | Bùi Ngọc Huy | Iteration 3 | 17/2/2024 | 23/2/2024 |  | complete
| Add Product To Cart | Medium | Iteration 3 | CE170981 | Bùi Ngọc Huy | Iteration 3 | 17/2/2024 | 23/2/2024 |  | complete
| Delete Product | Simple | Iteration 3 | CE170981 | Bùi Ngọc Huy | Iteration 3 | 17/2/2024 | 23/2/2024 |  | complete
| Update Quantity | Medium | Iteration 3 | CE171653 | Phan Hoàng Phúc | Iteration 3 | 17/2/2024 | 23/2/2024 |  | complete
| View Cart | Simple | Iteration 3 | CE171653 | Phan Hoàng Phúc | Iteration 3 | 17/2/2024 | 23/2/2024 |  | complete
Product Management | Update Product | Medium | Iteration 4 | CE171653 | Phan Hoàng Phúc | Iteration 4 | 24/2/2024 | 29/2/2024 |  | complete
| Delete Product In Web | Simple | Iteration 4 | CE171653 | Phan Hoàng Phúc | Iteration 4 | 24/2/2024 | 29/2/2024 |  | complete
| Add New Product | Medium | Iteration 4 | CS171351 | Nguyễn Thị Ngà | Iteration 4 | 24/2/2024 | 29/2/2024 |  | complete
| View All Product Admin | Simple | Iteration 4 | CE170981 | Bùi Ngọc Huy | Iteration 4 | 24/2/2024 | 29/2/2024 |  | complete
| Product Statistics | Simple | Iteration 4 | CE171653 | Phan Hoàng Phúc | Iteration 4 | 24/2/2024 | 29/2/2024 |  | complete
Customer Management | Sort Customer | Simple | Iteration 5 | CS171351 | Nguyễn Thị Ngà | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Search Customer By Name | Simple | Iteration 5 | CS171351 | Nguyễn Thị Ngà | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Search Customer By Phone | Simple | Iteration 5 | CS171351 | Nguyễn Thị Ngà | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| View All Customer | Simple | Iteration 5 | CS171351 | Nguyễn Thị Ngà | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Sort New Customer | Simple | Iteration 5 | CS171351 | Nguyễn Thị Ngà | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
Order Management | Filter Waiting Order | Simple | Iteration 5 | CE161080 | Nguyễn Thanh Quang Duy | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Filter Accepted Order | Simple | Iteration 5 | CE161080 | Nguyễn Thanh Quang Duy | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| View Order List For Comfirmation | Simple | Iteration 5 | CE161080 | Nguyễn Thanh Quang Duy | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| View Order List | Simple | Iteration 5 | CE161080 | Nguyễn Thanh Quang Duy | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Search By NameCustomer | Simple | Iteration 5 | CE161080 | Nguyễn Thanh Quang Duy | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Search By PhoneCustomer | Simple | Iteration 5 | CE161080 | Nguyễn Thanh Quang Duy | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Cancel Order Admin | Medium | Iteration 5 | CE161080 | Nguyễn Thanh Quang Duy | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Accept Order Admin | Medium | Iteration 5 | CE161080 | Nguyễn Thanh Quang Duy | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| View Order Details admin | Simple | Iteration 5 | CE161080 | Nguyễn Thanh Quang Duy | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| View Order History | Simple | Iteration 5 | CE170981 | Bùi Ngọc Huy | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
Statistical Management | Customer Count | Simple | Iteration 5 | CE170981 | Bùi Ngọc Huy | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Analysis by Date/Month/Year | Simple | Iteration 5 | CE171653 | Nguyễn Thị Ngà | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Total Orders | Simple | Iteration 5 | CE171653 | Phan Hoàng Phúc | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Customer Statistics | Simple | Iteration 5 | CS171351 | Nguyễn Thị Ngà | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Total Sales Order Value | Simple | Iteration 5 | CE161080 | Nguyễn Thanh Quang Duy | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Order Status Analysis | Simple | Iteration 5 | CE171653 | Phan Hoàng Phúc | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Product Analysis by Type | Simple | Iteration 5 | CE171653 | Phan Hoàng Phúc | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Total Quantity | Simple | Iteration 5 | CS171351 | Nguyễn Thị Ngà | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
| Total Value Of Goods | Simple | Iteration 5 | CS171351 | Nguyễn Thị Ngà | Iteration 5 | 2024-01-03 | 2024-09-03 |  | complete
-- | -- |  |  | -- | --