## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Deadline | Date of extension | Status | Actual | Updated | Update Details
1 | Update Profile | Update Profile | Customer, Admin | The main page of the application, allowing users to access the system by logging in. Users can enter their login information (email and password) to access other features of the application. | Bùi Ngọc Huy | 2024-02-02 | 2024-09-02 | Done | iter1 | iter1
2 | Change Password | Change Password | Customer, Admin | This is short descripiton for the screen/function (2-3 sentences) | Bùi Ngọc Huy | 2024-02-02 | 2024-09-02 | Done | iter1 | iter1
3 | Logout | Logout | Customer, Admin | This is short descripiton for the screen/function (2-3 sentences) | Phan Hoàng Phúc | 2024-02-02 | 2024-09-02 | Done | iter1 | iter1
4 | Forget Password | Forget Password | Customer, Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Phan Hoàng Phúc | 2024-02-02 | 2024-09-02 | Done | iter1 | iter1
5 | Login | Login | Guest, Customer, Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Phan Hoàng Phúc | 2024-02-02 | 2024-09-02 | Done | iter1 | iter1
6 | Register Account | Register Account | Guest, Customer, Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Phan Hoàng Phúc | 2024-02-02 | 2024-09-02 | Done | iter1 | iter1
7 | Search By Name | Search By Name | Guest, Customer, Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Nguyễn Thị Ngà | 2024-02-02 | 2024-09-02 | Done | iter1 | iter1
8 | View All Product | View All Product | Guest, Customer, Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Nguyễn Thị Ngà | 2024-02-02 | 2024-09-02 | Done | iter1 | iter1
9 | View Product By Caterory | View Product By Caterory | Guest, Customer, Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Nguyễn Thị Ngà | 2024-02-02 | 2024-09-02 | Done | iter1 | iter1
10 | View Best Seller | View Best Seller | Guest, Customer, Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Bùi Ngọc Huy | 2024-10-02 | 16/2/2024 | Done | iter2 | iter2
11 | View Newest Product | View Newest Product | Guest, Customer, Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Phan Hoàng Phúc | 2024-10-02 | 16/2/2024 | Done | iter2 | iter2
12 | Filter By Price | Filter By Price | Guest, Customer, Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Phan Hoàng Phúc | 2024-10-02 | 16/2/2024 | Done | iter2 | iter2
13 | Sort By Price | Sort By Price | Guest, Customer, Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Nguyễn Thị Ngà | 2024-10-02 | 16/2/2024 | Done | iter2 | iter2
14 | Sort By Newest Product | Sort By Newest Product | Guest, Customer, Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Nguyễn Thị Ngà | 2024-10-02 | 16/2/2024 | Done | iter2 | iter2
15 | Sort By Letter | Sort By Letter | Guest, Customer, Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Nguyễn Thị Ngà | 2024-10-02 | 16/2/2024 | Done | iter2 | iter2
16 | Cancel Order | Cancel Order | Customer | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Nguyễn Thanh Quang Duy | 2024-10-02 | 16/2/2024 | Done | iter2 | iter2
17 | Buy Product | Buy Product | Customer | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Nguyễn Thanh Quang Duy | 2024-10-02 | 16/2/2024 | Done | iter2 | iter2
18 | View Order List | View Order List | Customer | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Bùi Ngọc Huy | 2024-10-02 | 16/2/2024 | Done | iter2 | iter2
19 | View Order Details | View Order Details | Customer | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Bùi Ngọc Huy | 17/2/2024 | 23/2/2024 | Done | iter3 | iter3
20 | View Product Details | View Product Details | Customer, Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Bùi Ngọc Huy | 17/2/2024 | 23/2/2024 | Done | iter3 | iter3
21 | Add Product To Cart | Add Product To Cart | Customer | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Bùi Ngọc Huy | 17/2/2024 | 23/2/2024 | Done | iter3 | iter3
22 | Delete Product | Delete Product | Customer | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Bùi Ngọc Huy | 17/2/2024 | 23/2/2024 | Done | iter3 | iter3
23 | Edit Product | Edit Product | Customer | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Phan Hoàng Phúc | 17/2/2024 | 23/2/2024 | Done | iter3 | iter3
24 | View Cart | View Cart | Customer | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Phan Hoàng Phúc | 17/2/2024 | 23/2/2024 | Done | iter3 | iter3
25 | Update Product | Update Product | Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Phan Hoàng Phúc | 24/2/2024 | 29/2/2024 | Done | iter4 | iter4
26 | Delete Product In Web | Delete Product In Web | Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Phan Hoàng Phúc | 24/2/2024 | 29/2/2024 | Done | iter4 | iter4
27 | Add New Product | Add New Product | Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Nguyễn Thị Ngà | 24/2/2024 | 29/2/2024 | Done | iter4 | iter4
28 | View All Product Admin | View All Product Admin | Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Bùi Ngọc Huy | 24/2/2024 | 29/2/2024 | Done | iter4 | iter4
29 | View Product Detail Admin | View Product Detail Admin | Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Bùi Ngọc Huy | 24/2/2024 | 29/2/2024 | Done | iter4 | iter4
30 | Product Statistics | Product Statistics | Admin | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Phan Hoàng Phúc | 24/2/2024 | 29/2/2024 | Done | iter4 | iter4
31 | View Product Detail | View Product Detail | User | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Tử Vinh |  |  | To Do | iter4 | none
31 | Sort Customer | Sort Customer | Admin | Allows admin to sort customers as desired | Nguyễn Thị Ngà | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
32 | Search Customer By Name | Search Customer By Name | Admin | Allows admin to search for customers based on name | Nguyễn Thị Ngà | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
33 | Search Customer By Phone | Search Customer By Phone | Admin | Allows admin to search for customers based on phone number | Nguyễn Thị Ngà | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
34 | View All Customer | View All Customer | Admin | Allow admin to view all customers who have placed orders in the system | Nguyễn Thị Ngà | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
35 | Sort New Customer | Sort New Customer | Admin | Allows admin to sort newest customers first | Nguyễn Thị Ngà | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
36 | Filter Waiting Order | Filter Waiting Order | Admin | Allows users to access detailed information about a specific product. | Nguyễn Thanh Quang Duy | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
37 | Filter Accepted Order | Filter Accepted Order | Admin | Allows users to remove a product from the web platform. | Nguyễn Thanh Quang Duy | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
38 | View Order List For Comfirmation | View Order List For Comfirmation | Admin | Allow user to view their order history | Nguyễn Thanh Quang Duy | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
39 | View Order List | View Order List | Admin | Allow user to view their order history | Nguyễn Thanh Quang Duy | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
40 | Search By NameCustomer | Search By NameCustomer | Admin | Allow admin to search customer by name | Nguyễn Thanh Quang Duy | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
41 | Search By PhoneCustomer | Search By PhoneCustomer | Admin | Allow admin to search customer by phone | Nguyễn Thanh Quang Duy | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
42 | Cancel Order Admin | Cancel Order Admin | Admin | Allow admin to cancel customer order | Nguyễn Thanh Quang Duy | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
43 | Accept Order Admin | Accept Order Admin | Admin | Allow admin to accept customer order | Nguyễn Thanh Quang Duy | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
44 | View Order Details admin | View Order Details admin | Admin | Allow admin to view detail of customer's order | Nguyễn Thanh Quang Duy | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
45 | View Order History | View Order History | Customer | Allow user to view their order history | Bùi Ngọc Huy | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
46 | Customer Count | Customer Count | Admin | Allow admin to view the cout customer statistics | Bùi Ngọc Huy | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
47 | Analysis by Date/Month/Year | Analysis by Date/Month/Year | Admin | Allow admin to view analysis by day/month/year purchase | Nguyễn Thị Ngà | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
48 | Total Orders | Total Orders | Admin | Allow admin to view the total order | Phan Hoàng Phúc | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
49 | Customer Statistics | Customer Statistics | Admin | Allow admin to view all customer Statistics | Nguyễn Thị Ngà | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
50 | Total Sales Order Value | Total Sales Order Value | Admin | Allow admin to view the total sales order value | Nguyễn Thanh Quang Duy | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
51 | Order Status Analysis | Order Status Analysis | Admin | Allow admin to view the order status analysis | Phan Hoàng Phúc | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
52 | Product Analysis by Type | Product Analysis by Type | Admin | Allow admin to view product analysis by type | Phan Hoàng Phúc | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
53 | Total Quantity | Total Quantity | Admin | Allow admin to view the total quantity | Nguyễn Thị Ngà | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5
54 | Total Value Of Goods | Total Value Of Goods | Admin | Allow admin to view the total value of goods | Nguyễn Thị Ngà | 2024-01-03 | 2024-09-03 | Done | iter5 | iter5

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Profile | Update Profile | Users can update personal information on the system such as address and phone number | Bùi Ngọc Huy | Done | II.3 | III.5
2 | Profile | Update Password | Users can update new passwords for more convenient login | Bùi Ngọc Huy | Done | II.1 | III.4
3 | Login | Login | The user logs into the system after successfully creating an account | Phan Hoàng Phúc | Done | II.1 | III.4
4 | Login | Logout | Users can log out of the system and log in with another account | Phan Hoàng Phúc | Done | II.1 | III.4
5 | Login | Forgot Password | Users can authenticate to retrieve their password if they forget their old password | Phan Hoàng Phúc | Done | II.1 | III.4
6 | Register Account | Register | Users can create new accounts based on email | Phan Hoàng Phúc | Done | II.1 | III.4
7 | Search Product | Search Product | Users can search for products by entering the product name in the search box | Nguyễn Thị Ngà | Done | II.1 | III.4
8 | View All Product | View All Product | Users can view all products of the system without logging in | Nguyễn Thị Ngà | Done | II.1 | III.4
9 | Caterory Manager | View Product By Caterory | Users view products based on the name of the desired brand | Nguyễn Thị Ngà | Done | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | View Best Seller | View Best Seller | Displays the top-selling products on the platform. | Bùi Ngọc Huy | Done | II.3 | III.5
2 | View Newest Product | View Newest Product | Shows the latest additions to the product catalog. | Phan Hoàng Phúc | Done | II.1 | III.4
3 | Filter By Price | View Newest Product | Allows users to narrow down product options based on price range. | Phan Hoàng Phúc | Done | II.1 | III.4
4 | Sort By Price | Sort By Price | Arranges product listings based on price, typically from lowest to highest or vice versa. | Nguyễn Thị Ngà | Done | II.1 | III.4
5 | Sort By Newest Product | Sort By Newest Product | Organizes products based on their date of addition, with the newest items appearing first. | Nguyễn Thị Ngà | Done | II.1 | III.4
6 | Sort By Letter | Sort By Letter | Sorts products alphabetically, typically by product name or title. | Nguyễn Thị Ngà | Done | II.1 | III.4
7 | Cancel Order | Cancel Order | Enables users to cancel a placed order before it is processed. | Nguyễn Thanh Quang Duy | Done | II.1 | III.4
8 | Buy Product | Buy Product | Allows users to initiate the purchase of a selected product. | Nguyễn Thanh Quang Duy | Done | II.1 | III.4
9 | View Order List | View Order List | Provides users with a list of their past and current orders. | Bùi Ngọc Huy | Done | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | View Product Details | View Product Details | Users can view detailed information about a specific product on the website or application. | Bùi Ngọc Huy | Done | II.3 | III.5
2 | Add Product To Cart | Add Product To Cart | Users can add a product to their cart for later purchase. | Bùi Ngọc Huy | Done | II.1 | III.4
3 | Delete Product | Delete Product | Users can remove a product from the cart if they no longer wish to purchase it. | Bùi Ngọc Huy | Done | II.1 | III.4
4 | Edit product | Edit product | Users can update the quantity, size of a product in the cart before checkout. | Phan Hoàng Phúc | Done | II.1 | III.4
5 | View Cart | View Cart | Allows users to see the items currently in their shopping cart. | Phan Hoàng Phúc | Done | II.1 | III.4
6 | Update Product | Update Product | Enables users to modify details or properties of a product. | Tử Vinh | To Do | II.1 | III.4
7 | Delete Product In Web | Delete Product In Web | Allows users to remove a product from the web platform. | Tử Vinh | To Do | II.1 | III.4
8 | Add New Product | Add New Product | Permits users to add a new product to the system. | Tử Vinh | To Do | II.1 | III.4
9 | View All Product Admin | View All Product Admin | Provides administrators with the ability to view a list of all products. | Tử Vinh | To Do | II.1 | III.4
10 | View Product Detail Admin | View Product Detail Admin | Allows administrators to access detailed information about a specific product. | Tử Vinh | To Do | II.1 | III.4
11 | Product Statistics | Product Statistics | Provides statistical data and insights related to product performance. | Tử Vinh | To Do | II.1 | III.4
12 | View Product Detail | View Product Detail | Allows users to access detailed information about a specific product. | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Update Product | Update Product | Allows users to remove a product from the web platform. | Phan Hoàng Phúc | Done | II.3 | III.5
2 | Add New Product | Add New Product | Permits users to add a new product to the system. | Nguyễn Thị Ngà | Done | II.1 | III.4
3 | View All Products (Admin) | View All Products (Admin) | Provides administrators with the ability to view a list of all products. | Bùi Ngọc Huy | Done | II.1 | III.4
4 | View Product Detail (Admin) | View Product Detail (Admin) | Allows administrators to access detailed information about a specific product. | Bùi Ngọc Huy | Done | II.1 | III.4
5 | Product Statistics | Product Statistics | Provides statistical data and insights related to product performance. | Bùi Ngọc Huy | Done | II.1 | III.4
6 | View Product Detail | View Product Detail | Allows users to access detailed information about a specific product. | Bùi Ngọc Huy | Done | II.1 | III.4
7 | Delete Product In Web | Delete Product In Web | Allows users to remove a product from the web platform. | Phan Hoàng Phúc | Done | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter5
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Sort Customer | Sort Customer | Allows admin to sort customers as desired | Nguyễn Thị Ngà | Done | II.3 | III.5
2 | Search Customer By Name | Search Customer By Name | Allows admin to search for customers based on name | Nguyễn Thị Ngà | Done | II.1 | III.4
3 | Search Customer By Phone | Search Customer By Phone | Allows admin to search for customers based on phone number | Nguyễn Thị Ngà | Done | II.1 | III.4
4 | View All Customer | View All Customer | Allow admin to view all customers who have placed orders in the system | Nguyễn Thị Ngà | Done | II.1 | III.4
5 | Sort New Customer | Sort New Customer | Allows admin to sort newest customers first | Nguyễn Thị Ngà | Done | II.1 | III.4
6 | Filter Waiting Order | Filter Waiting Order | Allows users to access detailed information about a specific product. | Nguyễn Thanh Quang Duy | Done | II.1 | III.4
7 | Filter Accepted Order | Filter Accepted Order | Allows users to remove a product from the web platform. | Nguyễn Thanh Quang Duy | Done | II.1 | III.4
8 | View Order List For Comfirmation | View Order List For Comfirmation | Allow user to view their order history | Nguyễn Thanh Quang Duy | Done | II.3 | III.5
9 | View Order List | View Order List | Allow user to view their order history | Nguyễn Thanh Quang Duy | Done | II.1 | III.4
10 | Search By NameCustomer | Search By NameCustomer | Allow admin to search customer by name | Nguyễn Thanh Quang Duy | Done | II.1 | III.4
11 | Search By PhoneCustomer | Search By PhoneCustomer | Allow admin to search customer by phone | Nguyễn Thanh Quang Duy | Done | II.1 | III.4
12 | Cancel Order Admin | Cancel Order Admin | Allow admin to cancel customer order | Nguyễn Thanh Quang Duy | Done | II.1 | III.4
13 | Accept Order Admin | Accept Order Admin | Allow admin to accept customer order | Nguyễn Thanh Quang Duy | Done | II.1 | III.4
14 | View Order Details admin | View Order Details admin | Allow admin to view detail of customer's order | Nguyễn Thanh Quang Duy | Done | II.1 | III.4
15 | View Order History | View Order History | Allow user to view their order history | Bùi Ngọc Huy | Done | II.3 | III.5
16 | Customer Count | Customer Count | Allow admin to view the cout customer statistics | Bùi Ngọc Huy | Done | II.1 | III.4
17 | Analysis by Date/Month/Year | Analysis by Date/Month/Year | Allow admin to view analysis by day/month/year purchase | Nguyễn Thị Ngà | Done | II.1 | III.4
18 | Total Orders | Total Orders | Allow admin to view the total order | Phan Hoàng Phúc | Done | II.1 | III.4
19 | Customer Statistics | Customer Statistics | Allow admin to view all customer Statistics | Nguyễn Thị Ngà | Done | II.1 | III.4
20 | Total Sales Order Value | Total Sales Order Value | Allow admin to view the total sales order value | Nguyễn Thanh Quang Duy | Done | II.1 | III.4
21 | Order Status Analysis | Order Status Analysis | Allow admin to view the order status analysis | Phan Hoàng Phúc | Done | II.1 | III.4
22 | Product Analysis by Type | Product Analysis by Type | Allow admin to view product analysis by type | Phan Hoàng Phúc | Done | II.1 | III.4
23 | Total Quantity | Total Quantity | Allow admin to view the total quantity | Nguyễn Thị Ngà | Done | II.1 | III.4
24 | Total Value Of Goods | Total Value Of Goods | Allow admin to view the total value of goods | Nguyễn Thị Ngà | Done | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document